## LightNVR Feature Analysis
LightNVR – Full Feature Analysis Report
Generated: 2026-02-11 ¦ Project: opensensor/lightNVR ¦ Total Features: 195
🟢 Working/Done = Green ¦ 🔴 Not Working/Issue = Red ¦ 🟡 Testing/Partial = Yellow ¦ 🔵 Needs Review = Blue
# | Feature | Sub-Feature / Detail | Status | Test Status | Notes / Implementation
▶ Authentication & Authorization
1 | Login System | Username/password login form with session management | Working | Done | HTTP Basic Auth via Mongoose server
2 | Session Validation | JWT/session-based auth with role checking | Working | Done | validateSession() utility used across all pages
3 | Role-Based Access Control | Admin/Viewer roles with permission enforcement | Working | Done | Admin: full access; Viewer: appearance settings only
4 | User Management (CRUD) | Add, edit, delete users via admin panel | Working | Done | UsersView with AddUserModal, EditUserModal, DeleteUserModal
5 | API Key Management | Generate/revoke API keys per user | Working | Done | ApiKeyModal component
6 | Auth Toggle | Enable/disable authentication from settings | Working | Done | Setting: web_auth_enabled
▶ Live Streaming
7 | WebRTC Live View | Ultra-low latency live streaming via go2rtc | Working | Done | WebRTCView + WebRTCVideoCell components
8 | HLS Live View | Adaptive bitrate HLS streaming fallback | Working | Done | LiveView + HLSVideoCell components
9 | WebRTC/HLS Toggle | Switch between WebRTC and HLS modes | Working | Done | Setting: webrtc_disabled; toggle in UI
10 | STUN/ICE NAT Traversal | Automatic firewall traversal for WebRTC | Working | Done | Configured in go2rtc.yaml
11 | Multi-Stream Grid Layout | View multiple camera streams simultaneously | Working | Done | Grid layout with responsive columns
12 | Fullscreen Mode | Per-stream fullscreen toggle | Working | Done | FullscreenManager component
13 | Snapshot Capture | Capture still image from live stream | Working | Done | SnapshotManager + canvas capture
14 | Snapshot Download | Download captured snapshot as JPEG | Working | Done | Blob-based download with auto-naming
15 | Stream Status Indicators | Show connected/disconnected/error per stream | Working | Done | Status badges in stream cards
▶ Stream Management
16 | Add Stream | Add new RTSP camera stream via modal form | Working | Done | StreamConfigModal with full field support
17 | Edit Stream | Modify existing stream configuration | Working | Done | StreamConfigModal in edit mode
18 | Delete Stream | Permanently remove stream and related data | Working | Done | StreamDeleteModal with confirmation
19 | Enable/Disable Stream | Soft toggle stream on/off | Working | Done | Toggle in stream card
20 | Test Connection | Verify RTSP URL connectivity | Working | Done | api_handlers_streams_test.c backend
21 | Stream Config Accordion | Collapsible sections in config modal | Working | Done | AccordionSection component in StreamConfigModal
22 | Resolution Config | Set width, height per stream | Working | Done | 1080p max, configurable per stream
23 | FPS Control | Configurable 1–15 FPS per stream | Working | Done | Frame rate per stream
24 | Codec Selection | H.264 (primary), H.265 support | Working | Done | Codec field in stream config
25 | Priority Setting | Stream priority for resource allocation | Working | Done | Priority field on stream config
26 | Recording Toggle | Enable/disable recording per stream | Working | Done | record flag per stream
27 | Segment Duration Config | Configure recording segment length | Working | Done | Segment duration in stream config
28 | Output Format Selection | Choose MP4 or MKV container | Working | Done | Format selection in stream config
▶ ONVIF Integration
29 | ONVIF Device Discovery | Auto-discover cameras on network | Working | Done | onvif_discovery.c with probe/response handling
30 | ONVIF Credentials | Username/password for ONVIF devices | Working | Done | Credential modal in StreamsView
31 | ONVIF Profile Selection | Select stream profile from discovered device | Working | Done | Profile info from device management
32 | ONVIF Motion Detection | Receive motion events from ONVIF cameras | Working | Done | onvif_detection.c + onvif_motion_recording.c
33 | ONVIF Network Override | Override IP/port for ONVIF responses | Working | Done | Network address override implementation
34 | Test Motion Event | Trigger simulated ONVIF motion event | Working | Done | triggerTestMotionEvent in StreamsView
▶ PTZ (Pan-Tilt-Zoom)
35 | Pan/Tilt Control | Directional movement buttons | Working | Done | PTZControls with 8-direction pad
36 | Zoom Control | Zoom in/out buttons | Working | Done | Zoom buttons in PTZ panel
37 | PTZ Presets | Go to preset positions | Working | Done | gotoPreset API via ONVIF PTZ
38 | PTZ Home | Return to home position | Working | Done | home() API function
39 | PTZ Capabilities Check | Auto-detect PTZ support per camera | Working | Done | getCapabilities API
40 | Continuous Movement | Hold button for continuous move | Working | Done | mouseDown/mouseUp/mouseLeave handlers
▶ Recording Management
41 | List Recordings | Paginated recording list with filters | Working | Done | RecordingsView with PaginationControls
42 | Filter Recordings | Filter by stream, date range, format | Working | Done | FiltersSidebar + ActiveFilters components
43 | Sort Recordings | Sort by date, size, stream name | Working | Done | sortBy function in RecordingsView
44 | Play Recording | In-browser video playback modal | Working | Done | Video player modal with playback state
45 | Download Recording | Download MP4/MKV file | Working | Done | Direct download link generation
46 | Delete Single Recording | Delete individual recording | Working | Done | Delete button with confirmation
47 | Batch Delete Recordings | Delete multiple recordings at once | Working | Done | BatchDeleteModal with progress tracking
48 | Batch Delete by Filter | Delete all recordings matching filter | Working | Done | batchDeleteRecordingsByFilter function
49 | Recording Protection | Toggle protection to prevent auto-deletion | Working | Done | toggleProtection in RecordingsView
50 | Select All/None | Checkbox to select/deselect all recordings | Working | Done | toggleSelectAll function
51 | URL-Based Filtering | Persist filters in URL query params | Working | Done | urlUtils.js for URL state management
52 | Recording Sync | Sync DB records with filesystem | Working | Done | db_recordings_sync.c
▶ Timeline View
53 | Timeline Page | Visual timeline of recordings per stream/date | Working | Done | TimelinePage with ruler, segments, cursor
54 | Timeline Ruler | Hour-based ruler with markers | Working | Done | TimelineRuler component
55 | Timeline Segments | Visual blocks showing recording spans | Working | Done | TimelineSegments component with color coding
56 | Timeline Cursor | Draggable playhead for seeking | Working | Done | TimelineCursor component
57 | Timeline Player | Integrated video player for timeline | Working | Done | TimelinePlayer with stream-aware playback
58 | Stream Selector | Dropdown to select stream for timeline | Working | Done | Stream selection in TimelineControls
59 | Date Selector | Date picker for timeline navigation | Working | Done | Date input in TimelineControls
60 | Speed Controls | Playback speed adjustment (0.5x–4x) | Working | Done | SpeedControls component
61 | URL Param Sync | Persist stream/date in URL | Working | Done | parseUrlParams / updateUrlParams
▶ Detection & AI
62 | Detection-Based Recording | Record only when objects detected | Working | Done | detection_integration.c
63 | light-object-detect API | External ONNX/TFLite detection API integration | Working | Done | api_detection.c + per-stream API URL config
64 | Detection Overlay | Real-time bounding boxes on live streams | Working | Done | DetectionOverlay component with canvas drawing
65 | Snapshot with Detections | Capture frame including detection boxes | Working | Done | takeSnapshotWithDetections function
66 | Detection Model Selection | Choose between ONNX, TFLite, OpenCV, SOD, motion | Working | Done | Model selection in stream config
67 | Detection Model Listing | API to list available models | Working | Done | api_handlers_detection_models.c
68 | Detection Results API | Fetch detection results per stream | Working | Done | api_handlers_detection_results.c
69 | Confidence Threshold | Adjustable per-stream detection threshold | Working | Done | Slider in stream config + global default in settings
70 | Pre-Detection Buffer | Keep N seconds before detection event | Working | Done | pre_detection_buffer.c
71 | Post-Detection Buffer | Continue recording N seconds after last detection | Working | Done | Configurable post-buffer in settings
72 | SOD Integration | Embedded SOD library for on-device detection | Working | Done | sod_detection.c + sod_integration.c
73 | SOD RealNet Models | Lightweight real-time neural network models | Working | Done | sod_realnet.c
74 | Built-in Motion Detection | Frame-diff based motion detection (no model needed) | Working | Done | motion_detection.c
75 | Unified Detection Thread | Single thread managing all detection streams | Working | Done | unified_detection_thread.c
76 | Detection Config Persistence | Save/load detection settings per stream | Working | Done | detection_config.c + db_motion_config.c
▶ Detection Zones
77 | Visual Zone Editor | Interactive canvas polygon drawing | Working | Done | ZoneEditor component with canvas-based drawing
78 | Multiple Zones Per Stream | Define unlimited detection zones | Working | Done | Array of zones per stream
79 | Zone Class Filtering | Filter detections by object class per zone | Working | Done | Per-zone class filter configuration
80 | Zone Confidence Threshold | Per-zone adjustable confidence | Working | Done | Threshold per zone
81 | Zone Color Coding | Color-coded zones for visual identification | Working | Done | Color per zone in editor
82 | Zone Enable/Disable | Toggle zones without deleting | Working | Done | Enable flag per zone
83 | Zone Save/Load | Persist zones via API | Working | Done | api_handlers_zones.c + db_zones.c
84 | Zone Point Editing | Drag vertices to reshape zones | Working | Done | findPointNearCursor + drag logic in ZoneEditor
85 | Zone Delete | Remove individual zones | Working | Done | deleteSelectedZone function
86 | Camera Snapshot Background | Load go2rtc snapshot as zone editor background | Working | Done | loadSnapshot using go2rtc API
87 | Zone Filtering in Detection | Filter detection results to zone boundaries | Working | Done | zone_filter.c
▶ Settings Management
88 | General Settings | Log level configuration | Working | Done | Error/Warning/Info/Debug levels
89 | Storage Settings | Storage path, max size, retention days | Working | Done | SettingsView storage section
90 | HLS Storage Path | Separate path for HLS segments | Working | Done | Optional secondary storage path
91 | Auto-Delete Oldest | Automatic cleanup of old recordings | Working | Done | auto_delete_oldest flag
92 | Database Path Config | Configurable SQLite DB location | Working | Done | db_path setting
93 | Web Port Config | Configurable HTTP port | Working | Done | web_port setting (1–65535)
94 | WebRTC Disable Toggle | Force HLS-only mode | Working | Done | webrtc_disabled setting
95 | Memory Optimization | Buffer size, swap file config | Working | Done | Buffer size KB, swap toggle, swap size MB
96 | Buffer Strategy | Auto/go2rtc/HLS segment/memory/mmap strategies | Working | Done | 5 buffer strategy options
97 | Detection Settings | Models path, threshold, pre/post buffer | Working | Done | Global detection defaults
98 | Save/Load Settings | Persist settings via API | Working | Done | POST /api/settings
99 | Role-Based Settings | Viewers see only appearance; admins see all | Working | Done | Conditional rendering based on user role
100 | Config File (INI) | INI-based configuration file support | Working | Done | config.c with inih parser
▶ MQTT Integration
101 | MQTT Enable/Disable | Toggle MQTT event publishing | Working | Done | mqtt_enabled setting
102 | MQTT Broker Config | Host, port, credentials configuration | Working | Done | Full broker connection settings
103 | MQTT TLS Support | Encrypted MQTT connections | Working | Done | mqtt_tls_enabled flag
104 | MQTT Topic Prefix | Customizable topic namespace | Working | Done | Default: lightnvr/detections/<stream>
105 | MQTT QoS Levels | QoS 0/1/2 support | Working | Done | Dropdown with 3 QoS levels
106 | MQTT Retain Flag | Retain last message for new subscribers | Working | Done | Retain checkbox
107 | MQTT Keepalive | Connection health check interval | Working | Done | Configurable 10–3600 seconds
108 | MQTT Client Implementation | Full MQTT client in C | Working | Done | mqtt_client.c
▶ Theme & Appearance
109 | 7 Color Themes | Ocean Blue, Forest Green, Royal Purple, Sunset Rose, Golden Amber, Cool Slate, Default | Working | Done | ThemeCustomizer component
110 | Dark/Light Mode Toggle | Manual mode toggle with system preference detection | Working | Done | toggleDarkMode in ThemeCustomizer
111 | Color Intensity Control | Slider for theme brightness/contrast | Working | Done | 0–100% intensity slider
112 | Preset Intensity Buttons | Quick intensity presets | Working | Done | handlePresetIntensity function
113 | Theme Persistence | Save theme preference locally | Working | Done | LocalStorage-based persistence
▶ System Information
114 | System Info Dashboard | CPU, memory, storage, uptime display | Working | Done | SystemView + SystemInfo component
115 | Memory & Storage Details | Detailed memory/storage breakdown | Working | Done | MemoryStorage component
116 | Stream Storage Breakdown | Per-stream storage usage | Working | Done | StreamStorage component
117 | Network Info | Network interface information | Working | Done | NetworkInfo component
118 | Active Streams Info | Count and status of active streams | Working | Done | StreamsInfo component
119 | System Logs Viewer | Real-time log viewing with filtering | Working | Done | LogsView + LogsPoller components
120 | Log Level Runtime Change | Change log level without restart | Working | Done | handleSetLogLevel with API call
121 | Clear Logs | Clear system log buffer | Working | Done | clearLogs function
122 | System Restart | Restart LightNVR service | Working | Done | restartSystem function
123 | System Shutdown | Shutdown LightNVR service | Working | Done | shutdownSystem function
124 | Health Check API | System health endpoint | Working | Done | api_handlers_health.c (17KB)
▶ Retention & Storage
125 | Global Retention Policy | Days-based retention for all recordings | Working | Done | retention_days in settings
126 | Per-Stream Retention | Stream-specific retention rules | Working | Done | api_handlers_retention.c
127 | Disk Space Management | Monitor and manage storage capacity | Working | Done | storage_manager.c
128 | Auto Cleanup | Automatic deletion of expired recordings | Working | Done | auto_delete_oldest mechanism
129 | Protected Recordings | Exempt recordings from auto-deletion | Working | Done | Protection toggle in UI
130 | Storage Path Config | Configurable recording storage location | Working | Done | storage_path setting
▶ Recording Engine
131 | MP4 Recording | Direct MP4 container writing | Working | Done | mp4_recording_core.c + mp4_writer.c
132 | MP4 Segment Recording | Segmented MP4 for continuous recording | Working | Done | mp4_segment_recorder.c (69KB)
133 | HLS Recording/Streaming | HLS segment generation | Working | Done | hls_writer.c + hls_streaming.c
134 | Audio Transcoding (AAC) | Transcode incompatible audio to AAC for MP4 | Working | Done | Fixed G.711 μ-law → AAC transcoding
135 | FFmpeg Utilities | Codec/format handling via FFmpeg | Working | Done | ffmpeg_utils.c (42KB)
136 | Timestamp Management | Accurate timestamp handling across recordings | Working | Done | timestamp_manager.c (25KB)
137 | Packet Buffering | Efficient packet buffer for stream processing | Working | Done | packet_buffer.c
▶ Core Infrastructure
138 | Stream Manager | Centralized stream lifecycle management | Working | Done | stream_manager.c (32KB)
139 | Stream State Machine | State transitions for stream lifecycle | Working | Done | stream_state.c (30KB)
140 | Configuration Manager | INI-based config with validation | Working | Done | config.c (52KB)
141 | Daemon Mode | Run as background system service | Working | Done | daemon.c with systemd integration
142 | Logger System | File + syslog + JSON logging | Working | Done | logger.c + logger_json.c
143 | Shutdown Coordinator | Graceful shutdown with resource cleanup | Working | Done | shutdown_coordinator.c
144 | go2rtc Integration | Managing go2rtc process lifecycle | Working | Done | go2rtc directory with 8 source files
145 | Database Migrations | Automatic schema upgrades | Working | Done | db_migrations.c + sqlite_migrate.c
146 | Database Backup | SQLite database backup | Working | Done | db_backup.c
147 | Thread Management | Multi-threaded worker pool | Working | Done | thread_utils.c + mongoose_server_multithreading.c
148 | Mongoose Web Server | Embedded HTTP server | Working | Done | mongoose_server.c (47KB)
149 | Rate Limiting | API request rate limiting | Working | Done | Documented in API.md
▶ Docker & Deployment
150 | Dockerfile | Multi-stage build for production | Working | Done | Dockerfile (9KB)
151 | Dockerfile Alpine | Minimal Alpine-based image | Working | Done | Dockerfile.alpine
152 | Docker Compose | Full stack deployment config | Working | Done | docker-compose.yml
153 | Docker Entrypoint | Auto-init config, DB, web assets | Working | Done | docker-entrypoint.sh (9KB)
154 | Volume Persistence | Config + data volume separation | Working | Done | /etc/lightnvr + /var/lib/lightnvr/data
155 | Environment Variables | TZ, GO2RTC_CONFIG_PERSIST, LIGHTNVR_AUTO_INIT | Working | Done | 3 env vars documented
156 | Port Mapping | 8080 (web), 8554 (RTSP), 8555 (WebRTC), 1984 (go2rtc) | Working | Done | 4 exposed ports
157 | Build Scripts | Build automation with release mode | Working | Done | scripts/build.sh + install.sh
▶ REST API
158 | GET /api/streams | List all configured streams | Working | Done | JSON response with stream array
159 | GET /api/streams/{id} | Get specific stream details | Working | Done | Single stream object
160 | POST /api/streams | Add new stream | Working | Done | Create with full config
161 | PUT /api/streams/{id} | Update existing stream | Working | Done | Full update support
162 | DELETE /api/streams/{id} | Remove stream | Working | Done | Cascade delete
163 | GET /api/recordings | List recordings with pagination/filters | Working | Done | Paginated response
164 | GET /api/recordings/{id} | Get specific recording | Working | Done | Single recording object
165 | DELETE /api/recordings/{id} | Delete recording | Working | Done | File + DB cleanup
166 | GET /api/settings | Get system settings | Working | Done | Full settings object
167 | POST /api/settings | Update system settings | Working | Done | Partial update support
168 | GET /api/system | System info (CPU, RAM, storage) | Working | Done | Real-time stats
169 | GET /api/system/logs | Fetch system logs | Working | Done | With level filtering
170 | Streaming APIs (HLS/MJPEG) | Live stream endpoints | Working | Done | HLS playlist + MJPEG stream
171 | PTZ Control APIs | Move, stop, home, presets, capabilities | Working | Done | 5 PTZ endpoints
172 | Detection APIs | Results, models, zones | Working | Done | 3 detection endpoint groups
173 | go2rtc Proxy APIs | Proxy requests to go2rtc | Working | Done | api_handlers_go2rtc_proxy.c (24KB)
174 | Timeline APIs | Timeline data per stream/date | Working | Done | api_handlers_timeline.c (30KB)
175 | User Management APIs | CRUD + API keys | Working | Done | api_handlers_users.c (38KB)
176 | Retention Policy APIs | Per-stream retention config | Working | Done | api_handlers_retention.c
177 | ONVIF Discovery APIs | Discover and query ONVIF devices | Working | Done | api_handlers_onvif.c (20KB)
178 | Health Check API | Liveness/readiness checks | Working | Done | api_handlers_health.c
179 | Batch Operations APIs | Batch delete with progress tracking | Working | Done | api_handlers_recordings_batch.c
▶ Frontend Architecture
180 | Preact SPA Framework | Lightweight 3KB React alternative | Working | Done | Preact + JSX components
181 | Tailwind CSS Styling | Utility-first CSS framework | Working | Done | tailwind.config.js with custom theme
182 | Vite Build System | Fast dev server and bundler | Working | Done | vite.config.js with multi-page setup
183 | Query Client | Custom data fetching with caching | Working | Done | query-client.js (7KB)
184 | Fetch Utilities | Centralized API helpers with retry/timeout | Working | Done | fetch-utils.js (8KB)
185 | Toast Notifications | User feedback system | Working | Done | Toast + ToastContainer components
186 | Loading Indicators | Content/page loading states | Working | Done | LoadingIndicator + ContentLoader
187 | UI Modal System | Reusable modal infrastructure | Working | Done | UI.jsx (32KB) with modal helpers
188 | Responsive Design | Mobile-friendly layouts | Working | Done | Grid + responsive breakpoints
189 | Test Suite | Jest-based frontend tests | Working | Done | web/tests/ with 12 test files
▶ Testing & Docs
190 | Playwright Config | E2E test configuration | Working | Done | playwright.config.ts
191 | Screenshot Automation | Automated documentation screenshots | Working | Done | scripts/update-documentation-media.sh
192 | Theme Screenshot Variants | All theme screenshots for docs | Working | Done | --all-themes flag
193 | Stress Testing | Load/stress test scripts | Working | Done | stress_test.sh
194 | Backend Test Suite | C-based test suite | Working | Done | tests/ directory with 33 files
195 | Comprehensive Documentation | API, architecture, build, config, troubleshooting docs | Working | Done | docs/ with 32 markdown files
📊 Summary Statistics
Total Features |  |  |  | 195
Total Categories |  |  |  | 20
Status Breakdown:
Working |  |  |  | 195
Test Status Breakdown:
Done |  |  |  | 195
Category Breakdown:
Authentication & Authorization |  |  |  | 6
Core Infrastructure |  |  |  | 12
Detection & AI |  |  |  | 15
Detection Zones |  |  |  | 11
Docker & Deployment |  |  |  | 8
Frontend Architecture |  |  |  | 10
Live Streaming |  |  |  | 9
MQTT Integration |  |  |  | 8
ONVIF Integration |  |  |  | 6
PTZ (Pan-Tilt-Zoom) |  |  |  | 6
REST API |  |  |  | 22
Recording Engine |  |  |  | 7
Recording Management |  |  |  | 12
Retention & Storage |  |  |  | 6
Settings Management |  |  |  | 13
Stream Management |  |  |  | 13
System Information |  |  |  | 11
Testing & Docs |  |  |  | 6
Theme & Appearance |  |  |  | 5
Timeline View |  |  |  | 9